Project Plan

### Phase P0 – Baseline & design (~now–Apr 5)

| ID | Task | Definition of done | Checklist |
| --- | --- | --- | --- |
| P0-1 | Freeze technology choices | Written decision: vector DB, embedding, LLM, API framework, deployment | Short comparison (1 page); pin versions |
| P0-2 | Architecture & data-flow diagram | Four logical services + request path + what varies per experiment | Diagram + ~200 words |
| P0-3 | Single-node RAG MVP | Upload / ingest → chunk → embed → retrieve → LLM answer | 3 manual Q&A tests pass consistently |
| P0-4 | Corpus & fixed query set | Reusable documents + queries for all experiments | ≥50 queries; script can scale to 1k / 10k / 100k chunks |
| P0-5 | Repo & runbook draft | README: install, run services, one demo path | Someone else can reproduce (peer smoke test) |

### Phase P1 – Service split, deployment, observability (~Apr 6–Apr 12)

| ID | Task | Definition of done | Checklist |
| --- | --- | --- | --- |
| P1-1 | Split into four service roles | API / Embedding / Vector search / LLM as separate processes or containers | Document REST or gRPC contracts |
| P1-2 | Docker Compose (or minimal K8s) | One command brings full stack up | .env.example; document ports & dependencies |
| P1-3 | Bulk index builder | Load 1k / 10k / 100k chunks into vector store | CLI flag e.g. --num-chunks; log build time & footprint |
| P1-4 | Per-request timing | Stages: embed, retrieve, LLM, total | Logs or CSV export; optional Prometheus metrics |
| P1-5 | Health checks & errors | Timeouts; behavior when LLM is down | Clear HTTP status / error body; no silent failures under load |
| P1-6 | Baseline smoke numbers | Know rough end-to-end latency at low concurrency | One row of numbers as baseline for experiments |

### Phase P2 – Three scalability experiments (~Apr 13–Apr 19)

| ID | Task | Definition of done | Checklist |
| --- | --- | --- | --- |
| E1 | Exp1: Concurrency 10 → 50 → 200 | Mean & P95 latency; error / timeout rate | Same query mix; each level ≥2–3 min steady state; table + plot |
| E2 | Exp2: Data 1k → 10k → 100k chunks | Retrieve (and/or E2E) latency; memory or index size | Only data size changes; document hardware |
| E3 | Exp3: Horizontal scale 1 → 2 → 4 instances | Throughput (RPS); mean & P95 latency | State which tier scaled (e.g. API+embed or LLM); discuss linearity |
| E2-tool | Load-test harness | k6 / Locust / wrk reproducible | Params: concurrency, duration, base URL; save raw outputs |
| E2-analysis | Bottleneck write-up | ~1 page: dominant stage; whether scaling helped | Tied to architecture diagram |

### Phase P3 – Delivery & demo (through P2; finish by Apr 20)

| ID | Task | Definition of done | Checklist |
| --- | --- | --- | --- |
| D1 | Final report (PDF) | Intro, design, methods, results, conclusion, limitations | Clear plots; commands to reproduce |
| D2 | Presentation | Complete final presentation | Slides |

Use MeisterTask as Project management tool